## Sprint 1 Burndown
Backlog Item ID | User Stories / Requirements / Bugs | Estimated Time | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
D1 | Title Page | 0.1 | Day 8: 0.1
D2 | Table of Contents | 0.25 | Day 13: 0.5
D4 | Company Background & Current Environment | 0.75 | bar: Day 6
D5 | Problem Analysis (BPA) | 1 | Day 8: 1.5
D6 | Proposed System Objectives and Constraints | 0.5
D7 | Expected Benefits | 0.5 | Day 9: 1; Day 10: 0.5
D8 | Context Diagram | 1.5 | Day 8: 2
D10 | Use Case Diagram | 1.5 | Day 6: 3; Day 13: 1
S1-1 | Project Plan | 0.75 | Day 5: 0.5; Day 10: 0.5
S1-2 | Stakeholders | 0.25 | Day 10: 0.5
S1-3 | Functional & NonFunction Requirements | 1 | Day 8: 0.5; Day 9: 0.5
S1-4 | Executive Summary | 1 | bar: Day 13
1 | Install WordPress | 0.5 | Day 4: 0.5
2 | Install a chosen wordpress theme | 0.25 | Day 4: 0.25
3 | Install MongoDB on computer and WordPress | 0.5 | Day 4: 0.5
4 | Create WordPress Layouts for future information | 1 | bar: Day 5
5 | Input Company Information | 1 | Day 5: 0.5
| Team Charter | 1 | Day 8: 0.5; Day 10: 0.5
| Emails | 4 | Day 1: 0.5; Day 2: 0.5; Day 4: 0.5; Day 7: 0.5; Day 12: 0.5
| Meetings | 20 | 2 | 3 |  | 4.5 |  |  | 1 | 1 | 4 | 1 | 4 |  | 5 | 2
Remaining Effort |  | 37.35 | 34.85 | 31.35 | 31.35 | 25.1 | 23.1 | 19.1 | 17.6 | 12 | 6.5 | 3.5 | -0.5 | -1 | -8.5 | -10.5
Ideal Effort |  | 37.35 | 34.6821 | 32.0143 | 29.3464 | 26.6786 | 24.0107 | 21.3429 | 18.675 | 16.0071 | 13.3393 | 10.6714 | 8.0036 | 5.3357 | 2.6679 | -1.1546e-14

## Sprint 2 Burndown
Backlog Item ID | User Stories / Requirements / Bugs | Estimated Time | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
Remaining Effort |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ideal Effort |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Sprint 3 Burndown
Backlog Item ID | User Stories / Requirements / Bugs | Estimated Time | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
Remaining Effort |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ideal Effort |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Sprint 4 Burndown
Backlog Item ID | User Stories / Requirements / Bugs | Estimated Time | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
Remaining Effort |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ideal Effort |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Sprint 5 Burndown
Backlog Item ID | User Stories / Requirements / Bugs | Estimated Time | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
Remaining Effort |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ideal Effort |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Sprint 6 Burndown
Backlog Item ID | User Stories / Requirements / Bugs | Estimated Time | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
Remaining Effort |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ideal Effort |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0